## SOW Summary & Scope
STATEMENT OF WORK — COMMERCIAL TERMS & SCOPE BREAKDOWN
Project Name | Acme Corp — Omnichannel E-Commerce Modernization
Agreed Scope Value | 120000
Client | Acme Corporation
Effective Date | 2025-10-01
Section | Term Description / Clause Content
Original Scope (§1) | Magento to Shopify Plus migration, responsive storefront up to 2 Figma iterations, SAP Business One hourly sync, standard Shopify Payments USD, 10 days UAT.
Exclusions (§2) | Multi-currency/tax engines (Global-e), Loyalty/rewards, Subscription billing (Recharge), Native mobile apps, Data enrichment >5k SKUs, Design revisions >2.
Change Process (§3) | Written Change Request required prior to commencement. Rate: $150/hour.
Payment Terms (§4) | M1: $30k (Kickoff), M2: $36k (Storefront/ERP), M3: $36k (Catalog/UAT), M4: $18k (Go-live Net 15).
Notice Period (§5) | 7 calendar days for written rejection or milestone acceptance.